## Project Overview
Project | Jira Key | Description | Complexity | Team | Team Size | Expected Readiness | Fix Version | Has DB Migration | Has Dependencies
Project Atlas | ATLAS | Payment processing microservice upgrade | High | Team Alpha | 8 | Amber — Critical bugs open, incomplete docs | v3.2 — May 2026 Release | Yes | Yes — depends on Cipher, blocks Beacon
Project Beacon | BEACON | Customer portal UI redesign | Medium | Team Beta | 5 | Green/Amber — mostly done, blocked by Atlas | v2.0 — May 2026 Release | No | Yes — blocked by Atlas
Project Cipher | CIPHER | Security audit remediation (API gateway) | High | Team Gamma | 4 | Red — most work incomplete, no docs | v1.5 — May 2026 Release | No | Yes — blocks Atlas
Project Delta | DELTA | Internal reporting dashboard enhancement | Low | Team Delta | 3 | Green — fully ready | v4.1 — May 2026 Release | No | No

## Jira Tickets
Ticket Key | Project | Type | Summary | Status | Priority | Assignee | Fix Version | Links | Test Linked? | Milestone
ATLAS-101 | ATLAS | Story | Implement PCI-compliant tokenization for card data | Done | High | Dev1 | v3.2 | Test: ATLAS-201 | Yes | MVP
ATLAS-102 | ATLAS | Story | Migrate payment_transactions table to new schema | Done | High | Dev2 | v3.2 | Test: ATLAS-202, Blocks: BEACON-105 | Yes | MVP
ATLAS-103 | ATLAS | Story | Update payment gateway API integration | In Progress | High | Dev3 | v3.2 | Test: ATLAS-203, Depends on: CIPHER-104 | Yes | MVP
ATLAS-104 | ATLAS | Story | Add retry logic for failed payment callbacks | Done | Medium | Dev1 | v3.2 | Test: ATLAS-204 | Yes | MVP
ATLAS-105 | ATLAS | Story | Implement audit logging for payment events | To Do | Medium | Dev4 | v3.2 | None | No | MVP
ATLAS-106 | ATLAS | Bug | Race condition in concurrent payment processing | Open | Critical | Dev2 | v3.2 | — | N/A | MVP
ATLAS-107 | ATLAS | Bug | Memory leak in connection pool under load | Open | Blocker | Dev3 | v3.2 | — | N/A | MVP
ATLAS-108 | ATLAS | Task | Database migration script for payment_transactions | Done | High | Dev2 | v3.2 | — | N/A | MVP
ATLAS-109 | ATLAS | Task | Update API documentation for v3.2 endpoints | In Progress | Low | Dev4 | v3.2 | — | N/A | MVP
ATLAS-110 | ATLAS | Story | Add fraud detection webhook (LATE ADD) | To Do | High | Dev1 | v3.2 | None | No | M1 — scope creep
ATLAS-111 | ATLAS | Story | Support multi-currency payments (LATE ADD) | To Do | Medium | Dev2 | v3.2 | None | No | M1 — scope creep
ATLAS-201 | ATLAS | Test Execution | Test PCI tokenization — functional | Passed | High | QA1 | v3.2 | Story: ATLAS-101 | N/A | MVP
ATLAS-202 | ATLAS | Test Execution | Test schema migration — data integrity | Passed | High | QA1 | v3.2 | Story: ATLAS-102 | N/A | MVP
ATLAS-203 | ATLAS | Test Execution | Test gateway API — integration | Not Started | High | QA2 | v3.2 | Story: ATLAS-103 | N/A | MVP
ATLAS-204 | ATLAS | Test Execution | Test retry logic — edge cases | Passed | Medium | QA1 | v3.2 | Story: ATLAS-104 | N/A | MVP
BEACON-101 | BEACON | Story | Redesign customer dashboard layout | Done | High | Dev5 | v2.0 | Test: BEACON-201 | Yes | MVP
BEACON-102 | BEACON | Story | Implement responsive mobile view | Done | High | Dev6 | v2.0 | Test: BEACON-202 | Yes | MVP
BEACON-103 | BEACON | Story | Add dark mode theme support | Done | Medium | Dev5 | v2.0 | Test: BEACON-203 | Yes | MVP
BEACON-104 | BEACON | Story | Migrate to new component library | Done | High | Dev7 | v2.0 | Test: BEACON-204, Depends on: DELTA-102 | Yes | MVP/M3
BEACON-105 | BEACON | Story | Integrate with updated payment API | In Progress | High | Dev6 | v2.0 | Is blocked by: ATLAS-102 | No | MVP
BEACON-106 | BEACON | Bug | CSS rendering issue in Safari | Open | Medium | Dev7 | v2.0 | — | N/A | MVP
BEACON-201 | BEACON | Test Execution | Test dashboard layout — cross-browser | Passed | High | QA3 | v2.0 | Story: BEACON-101 | N/A | MVP
BEACON-202 | BEACON | Test Execution | Test mobile responsiveness | Passed | High | QA3 | v2.0 | Story: BEACON-102 | N/A | MVP
BEACON-203 | BEACON | Test Execution | Test dark mode — accessibility | Passed | Medium | QA3 | v2.0 | Story: BEACON-103 | N/A | MVP
BEACON-204 | BEACON | Test Execution | Test component library migration | Passed | High | QA3 | v2.0 | Story: BEACON-104 | N/A | MVP
CIPHER-101 | CIPHER | Story | Implement WAF rules for API gateway | In Progress | Critical | Dev8 | v1.5 | Test: CIPHER-201, Relates to: ATLAS-101 | Yes | MVP
CIPHER-102 | CIPHER | Story | Add mTLS authentication between services | To Do | High | Dev9 | v1.5 | None | No | MVP
CIPHER-103 | CIPHER | Story | Implement rate limiting on public endpoints | To Do | High | Dev8 | v1.5 | None | No | MVP (descoped M1)
CIPHER-104 | CIPHER | Story | Harden API gateway configuration | In Progress | Critical | Dev9 | v1.5 | Blocks: ATLAS-103 | No | MVP
CIPHER-105 | CIPHER | Bug | TLS certificate chain validation failing | Open | Blocker | Dev8 | v1.5 | — | N/A | MVP
CIPHER-106 | CIPHER | Bug | Rate limiter incorrectly counting internal traffic | Open | Critical | Dev9 | v1.5 | — | N/A | MVP
CIPHER-107 | CIPHER | Bug | JWT token validation bypass on edge case | Open | Blocker | Dev8 | v1.5 | — | N/A | MVP
CIPHER-201 | CIPHER | Test Execution | Test WAF rules — penetration test | Not Started | Critical | QA4 | v1.5 | Story: CIPHER-101 | N/A | MVP
DELTA-101 | DELTA | Story | Add export-to-PDF for monthly reports | Done | Medium | Dev10 | v4.1 | Test: DELTA-201 | Yes | MVP
DELTA-102 | DELTA | Story | Implement date range filter on dashboards | Done | Medium | Dev10 | v4.1 | Test: DELTA-202 | Yes | MVP
DELTA-103 | DELTA | Story | Add chart type selector (bar/line/pie) | Done | Low | Dev11 | v4.1 | Test: DELTA-203 | Yes | MVP
DELTA-104 | DELTA | Task | Update user documentation | Done | Low | Dev11 | v4.1 | — | N/A | MVP
DELTA-201 | DELTA | Test Execution | Test PDF export — formatting | Passed | Medium | QA5 | v4.1 | Story: DELTA-101 | N/A | MVP
DELTA-202 | DELTA | Test Execution | Test date filter — edge cases | Passed | Medium | QA5 | v4.1 | Story: DELTA-102 | N/A | MVP
DELTA-203 | DELTA | Test Execution | Test chart selector — rendering | Passed | Low | QA5 | v4.1 | Story: DELTA-103 | N/A | MVP

## Confluence Pages
Project | Page Title | Exists? | Content Quality | Last Modified | Key Content Notes | Milestone
ATLAS | ATLAS v3.2 — Release Plan | Yes | Complete | 3 days ago | Scope, dates, contacts, artifacts, env schedule | MVP
ATLAS | ATLAS v3.2 — Deployment Runbook | Yes | Incomplete | 2 weeks ago (stale) | Has deploy steps but MISSING rollback and verification sections | MVP
ATLAS | ATLAS v3.2 — Test Evidence | Yes | Complete | 1 day ago | Functional, integration, performance test results | MVP
ATLAS | ATLAS v3.2 — Rollback Procedure | No | Missing | — | Page does not exist — critical gap | MVP
ATLAS | ATLAS v3.2 — Release Notes | Yes | Draft | 5 days ago | Incomplete, marked work-in-progress | MVP
BEACON | BEACON v2.0 — Release Plan | Yes | Complete | 2 days ago | Full release plan | MVP
BEACON | BEACON v2.0 — Deployment Runbook | Yes | Complete | 1 day ago | All sections including rollback and verification | MVP
BEACON | BEACON v2.0 — Test Evidence | Yes | Complete | 1 day ago | Cross-browser, accessibility audit results | MVP
BEACON | BEACON v2.0 — Rollback Procedure | Yes | Complete | 3 days ago | Full rollback steps | MVP
BEACON | BEACON v2.0 — Release Notes | Yes | Complete | 2 days ago | Feature list and known issues | MVP
CIPHER | CIPHER v1.5 — Release Plan | Yes | Incomplete | 3 weeks ago (very stale) | Missing key dates and environment schedule | MVP
CIPHER | CIPHER v1.5 — Deployment Runbook | No | Missing | — | Page does not exist | MVP
CIPHER | CIPHER v1.5 — Test Evidence | No | Missing | — | Page does not exist | MVP
CIPHER | CIPHER v1.5 — Rollback Procedure | No | Missing | — | Page does not exist | MVP
CIPHER | CIPHER v1.5 — Release Notes | No | Missing | — | Page does not exist | MVP
DELTA | DELTA v4.1 — Release Plan | Yes | Complete | 4 days ago | Full release plan | MVP
DELTA | DELTA v4.1 — Deployment Runbook | Yes | Complete | 2 days ago | All sections complete | MVP
DELTA | DELTA v4.1 — Test Evidence | Yes | Complete | 1 day ago | All tests passed | MVP
DELTA | DELTA v4.1 — Rollback Procedure | Yes | Complete | 3 days ago | Straightforward rollback | MVP
DELTA | DELTA v4.1 — Release Notes | Yes | Complete | 2 days ago | Feature list | MVP
— | Release Runbook Template | Yes | Template | N/A | Defines required sections: Deploy Steps, Rollback, Verification, Contacts, Prerequisites | MVP

## ServiceNow Data
Record Type | Number | Short Description | Project/Team | State | Risk | CAB Decision | Scheduled Start | Scheduled End | Affected CIs | Milestone
Change Request | CHG0001001 | ATLAS v3.2 — Payment service upgrade | Atlas / Team Alpha | Assess (New) | High | Pending | 2026-05-16 22:00 | 2026-05-17 02:00 | payment-db-prod, api-gateway-prod, k8s-cluster-prod | MVP
Change Request | CHG0001002 | BEACON v2.0 — Customer portal redesign | Beacon / Team Beta | Assess (New) | Medium | Pending | 2026-05-16 22:00 | 2026-05-17 00:00 | customer-portal-prod, k8s-cluster-prod | MVP
Change Request | CHG0001003 | CIPHER v1.5 — API gateway hardening | Cipher / Team Gamma | Draft | High | Not Submitted | 2026-05-16 23:00 | 2026-05-17 03:00 | api-gateway-prod, k8s-cluster-prod | MVP
Change Request | CHG0001004 | DELTA v4.1 — Reporting dashboard enhancements | Delta / Team Delta | Scheduled (Approved) | Low | Approved | 2026-05-16 22:00 | 2026-05-16 23:00 | reporting-server-prod | MVP
Change Request | CHG0001050 | Database platform patching (EXTERNAL) | DBA Team | Scheduled | Medium | Approved | 2026-05-16 20:00 | 2026-05-16 21:30 | payment-db-prod | MVP — conflict
Change Request | CHG0001051 | Network firewall rule update (EXTERNAL) | Network Team | Scheduled | Low | Approved | 2026-05-16 21:00 | 2026-05-16 21:30 | api-gateway-prod | MVP — conflict
Change Task | CTASK0001001 | Run database migration script | Atlas | Open | — | — | — | — | payment-db-prod | MVP
Change Task | CTASK0001002 | Deploy atlas-payment-service:3.2.0 | Atlas | Open | — | — | — | — | k8s-cluster-prod | MVP
Change Task | CTASK0001003 | Execute smoke tests | Atlas | Open | — | — | — | — | — | MVP
Change Task | CTASK0001004 | Validate monitoring dashboards | Atlas | Open | — | — | — | — | — | MVP
Change Task | CTASK0001010 | Deploy delta-reporting:4.1.0 | Delta | Open | — | — | — | — | reporting-server-prod | MVP
Change Task | CTASK0001011 | Run regression tests | Delta | Open | — | — | — | — | — | MVP
CMDB CI | payment-db-prod | Production payment database | Atlas, Beacon (via Atlas) | Active | — | — | — | — | Used by: Atlas, External DBA team | MVP
CMDB CI | api-gateway-prod | Production API gateway | Atlas, Cipher, Beacon | Active | — | — | — | — | Used by: Atlas, Cipher, External Network team | MVP
CMDB CI | customer-portal-prod | Production customer portal | Beacon | Active | — | — | — | — | Used by: Beacon | MVP
CMDB CI | reporting-server-prod | Production reporting server | Delta | Active | — | — | — | — | Used by: Delta | MVP
CMDB CI | k8s-cluster-prod | Production Kubernetes cluster | All | Active | — | — | — | — | Shared by all projects | MVP
Incident | INC0001001 | Elevated error rate on payment API after deployment | Atlas | New | Sev-2 | — | — | — | Linked to: CHG0001001 | M4

## Historical Data (RAG)
Source System | Record Type | Month | Team/Project | Key Data Point | Outcome | Pattern for RAG | Milestone
Confluence | Post-Release Report | Mar 2026 | Team Alpha | Deployment duration: 90 min vs 45 min planned | Completed with issues | Duration overrun pattern | M2
Confluence | Retrospective | Mar 2026 | All | Phoenix team runbook incomplete — missed backup step | Action: Mandate runbook review 1 week prior | Documentation quality pattern | M2
Confluence | Post-Release Report | Feb 2026 | Team Alpha | Duration: 30 min vs 30 min planned | Completed successfully | Occasional on-time delivery | M2
Confluence | Post-Release Report | Jan 2026 | Team Alpha | Duration: 90 min vs 30 min planned. Connection pool issue. | Completed with issues — 12 min customer impact | Recurring overrun + incident pattern | M2
Confluence | Retrospective | Jan 2026 | Team Alpha | Pre-Prod didn't match Prod infrastructure sizing. Pool: 50 vs 200. | Action: Mandate env parity checks | Environment drift pattern | M2
Confluence | Post-Release Report | Dec 2025 | Team Alpha | Config mismatch discovered during deployment | Rolled back | Rollback due to config | M2
Confluence | Post-Release Report | Nov 2025 | Team Alpha | Duration: 60 min vs 30 min planned | Completed with issues | Duration overrun pattern | M2
Confluence | Post-Release Report | Oct 2025 | Team Beta | Duration: 22 min vs 25 min planned | Completed successfully | Consistently on-time | M2
Confluence | Post-Release Report | Sep 2025 | Team Beta | Duration: 18 min vs 20 min planned | Completed successfully | Consistently on-time | M2
Confluence | Post-Release Report | Aug 2025 | Team Beta | Duration: 20 min vs 25 min planned | Completed successfully | Consistently on-time | M2
ServiceNow | Closed CR | Mar 2026 | Team Alpha | CHG0000901 — Payment Service | Completed with issues | — | M2
ServiceNow | Closed CR | Mar 2026 | Team Phoenix | CHG0000902 — User Service | Rolled Back — DB timeout | Rollback pattern for DB migrations | M2
ServiceNow | Closed CR | Feb 2026 | Team Alpha | CHG0000801 — Payment Patch | Completed successfully | — | M2
ServiceNow | Closed CR | Jan 2026 | Team Alpha | CHG0000701 — Payment Major | Completed with issues — 1 incident | Incident during deployment pattern | M2
ServiceNow | Closed CR | Dec 2025 | Team Alpha | CHG0000601 — Payment Year-end | Rolled Back — config mismatch | Config-related rollback | M2
ServiceNow | Closed CR | Nov 2025 | Team Alpha | CHG0000501 — Payment Update | Completed with issues | Duration overrun | M2
ServiceNow | Closed CR | Oct 2025 | Team Beta | CHG0000401 — Portal Accessibility | Completed successfully | Clean record | M2
ServiceNow | Closed CR | Feb 2026 | Team Beta | CHG0000802 — Portal Hotfix | Completed successfully | Clean record | M2
ServiceNow | Closed CR | Mar 2026 | Team Beta | CHG0000903 — Portal Update | Completed successfully | Clean record | M2

## Dependency Map
Source Ticket | Source Project | Link Type | Target Ticket | Target Project | Dependency Reason | Conflict Risk | Milestone
ATLAS-102 | ATLAS | blocks | BEACON-105 | BEACON | Beacon's payment integration depends on Atlas's new schema | Medium — late Atlas delivery blocks Beacon | MVP
CIPHER-104 | CIPHER | blocks | ATLAS-103 | ATLAS | Atlas's gateway update depends on Cipher's hardening | High — Cipher is significantly behind | MVP
CIPHER-101 | CIPHER | relates to | ATLAS-101 | ATLAS | Both modify API gateway configuration | Medium — config conflict risk | M3
BEACON-104 | BEACON | depends on | DELTA-102 | DELTA | Beacon's component library uses Delta's date filter | Low — Delta is complete | M3
CHG0001050 (External) | DBA Team | shared CI | CHG0001001 (Atlas) | ATLAS | Both modify payment-db-prod | High — DB patching before Atlas migration | MVP
CHG0001051 (External) | Network Team | shared CI | CHG0001003 (Cipher) | CIPHER | Both affect api-gateway-prod | Medium — firewall change before gateway hardening | MVP

## CI-CD Pipelines (M4)
Pipeline Name | Project | Stages | Expected Duration | Test Scenario | Expected Agent Behavior | Milestone
atlas-payment-deploy | Atlas | Build → Test → Deploy-PreProd → Approve → Deploy-Prod → Smoke-Test | 45 min | Slow stage: Deploy-Prod takes 30 min instead of 10 | Agent alerts duration threshold. RAG retrieves Team Alpha overrun history. | M4
beacon-portal-deploy | Beacon | Build → Test → Deploy-PreProd → Approve → Deploy-Prod → Verify | 25 min | Normal: All stages complete on time | Dashboard shows green progress. | M4
cipher-gateway-deploy | Cipher | Build → Security-Scan → Test → Deploy-PreProd → Approve → Deploy-Prod → Pen-Test | 60 min | Failed stage: Security-Scan fails | Agent alerts pipeline failure. Dashboard shows Red for step. | M4
delta-reporting-deploy | Delta | Build → Test → Deploy-Prod → Verify | 15 min | Normal: Quick clean deployment | Dashboard shows green, first to complete. | M4

## RBAC Test Users (M5)
Username | Display Name | Role | Scope | What They Should See | What They Should NOT See
rm_alice | Alice Chen | Release Manager | All projects | Full access: all dashboards, intake decisions, Go/No-Go, deployment monitoring, reports, configuration | Nothing restricted
pl_bob | Bob Martinez | Project Team Lead | Atlas only | Atlas intake, scorecard, Go/No-Go recommendation. Own project data only. | Other projects' data, system config, CAB decisions for other teams
pl_carol | Carol Singh | Project Team Lead | Beacon only | Beacon intake, scorecard, Go/No-Go recommendation. | Other projects' data, system config
cab_dave | Dave Williams | CAB Member | All (read-only) | All project data (read-only), can record CAB decisions | Cannot modify intake, cannot update deployment status
devops_eve | Eve Thompson | DevOps Engineer | Deployment ops | Deployment status updates, rollback notifications, pipeline monitoring | Cannot modify intake decisions, release scheduling
exec_frank | Frank Rodriguez | Executive Viewer | Dashboards only | Summary dashboards, executive reports, program health metrics | No operational detail, no actions
admin_grace | Grace Kim | System Administrator | System config | MCP server config, user roles, integration settings, system health | Cannot make release decisions

## Setup Checklist
Milestone | Tool | Setup Task | Record Count | Status
MVP | Jira | Create 4 Jira projects (ATLAS, BEACON, CIPHER, DELTA) | 4 projects
MVP | Jira | Create Fix Versions in each project | 4 Fix Versions
MVP | Jira | Create story/bug/task tickets across all projects | 25+ tickets
MVP | Jira | Create test execution tickets linked to stories (with intentional gaps) | 10+ test tickets
MVP | Jira | Create cross-project links (ATLAS blocks BEACON, CIPHER blocks ATLAS) | 2 cross-links
MVP | Confluence | Create Release Management space | 1 space
MVP | Confluence | Create project doc pages (varying completeness) | 20 pages
MVP | Confluence | Create Runbook Template page | 1 template
MVP | ServiceNow | Create Change Requests in different states | 4 CRs + 2 external
MVP | ServiceNow | Create Change Tasks under Atlas and Delta CRs | 6 tasks
MVP | ServiceNow | Create CMDB Configuration Items | 5 CIs
M1 | Jira | Add late stories to Atlas Fix Version (scope creep) | 2 tickets
M1 | Jira | Descope story from Cipher Fix Version | 1 removal
M1 | Jira | Reopen BEACON-101 (status regression) | 1 status change
M2 | Confluence | Create 8 months of historical release plan pages | 8 pages
M2 | Confluence | Create 8 months of historical post-release report pages | 8 pages
M2 | Confluence | Create 8 months of historical retrospective pages | 8 pages
M2 | Confluence | Embed Team Alpha overrun pattern in historical data | Multiple references
M2 | Confluence | Embed Team Beta reliability pattern in historical data | Multiple references
M2 | ServiceNow | Create 10 historical closed Change Requests with outcomes | 10 CRs
M3 | Jira | Add additional cross-project dependency links | 4+ new links
M3 | ServiceNow | Update CMDB CIs with shared project references | 2 CI updates
M4 | CI/CD | Configure pipeline definitions for 4 projects | 4 pipelines
M4 | CI/CD | Prepare test scenarios (normal, slow, failed, incident) | 4 scenarios
M4 | ServiceNow | Create test Incident INC0001001 | 1 incident
M5 | All | Create 12 months synthetic release outcome data | 12 monthly records
M5 | All | Create team performance summary data | 4 team records
M5 | Platform | Create 7 test user accounts for RBAC roles | 7 users